Les Miserables schedule list

Please note that some of the dates may be subject to alteration,

this is what is expected as we go into rehearsals.

Please be on time for rehearsals, and if you are ill or unable to attend a date, please make sure Laura knows – either post on the facebook cast page, or text 07855 090589. Everyone else relies on you to be professional at all times, just as you rely on everybody else. If you miss over a third of rehearsals, or miss rehearsals without letting us know, your role may be re-cast.

Please put the dates in your diary now!

Rehearsals

Main rehearsals are every Wednesday evening at the Chestnut Heights centre. Please arrive by 7pm for group notices, so that we can start promptly. As this is a big show, expect to be there until around 10pm. (Cast playing Petit Gervais and Little Cosette may leave after Act 1, at around 9pm)

Some rehearsals will also be called for Sunday afternoons at the same venue, 1.30-4pm. Expect there to be three Sundays where all are required (July 28, August 4th and Sept 1st), however there may be more if the cast are felt to require extra rehearsal time, or for a specific scene.

Please always bring your script, a pen, and your diary to all rehearsals.

We expect to have scripts down (all lines learned) by the first week of August, because it is a lot easier to rehearse without scripts in your hands. There will be prizes for those who do it before.

Shows

Main shows will take place around Torbay between September 19th- 22nd.

Thurs 19th – Paignton (evening, cast and crew need to arrive for 4.30/ 5pm)

Fri 20th – Goodrington St George’s hall, cast and crew to arrive for 5pm

Sat 21sth – Brixham, matinee and evening, cast and crew to arrive by 1pm

Sun 22nd  – Torquay, matinee, cast and crew to arrive by 1pm

There are also various publicity stunts planned; these are very important to create public awareness of the shows, (this is not a cheap show, we need to get “full houses”!) display the casts’ acting skills, and create good PR with other local groups. Please attend as many as is possible!

Publicity events

These are the current ones, there may be others as well. Wherever possible we will be encouraging lifts and car-shares to get cast around to these, which will be arranged at rehearsals.

Cockington Village and Brixham Town promo photoshoot –  This is the main promo photoshoot for the show, we intend to do a promo shoot of the cast in Brixham town centre, and also do character photos at Cockington village. This date is flexible but will take place as soon as possible, within June and requires all major cast (and as many others as possible).

Paignton Carnival Parade – Weds July 31st (finalised and booked). Meeting at Paignton Green for 6pm.

Carnival parade entry The Cast of Les Miserables . We won Second Place and a fair bit of money for the group last year (all helps with show budget), let’s go for first place this year!

Brixham Farmers Market – Sunday August 11th, as above. 1- 3pm “revolutionary rally”in town centre, As many cast as can make it needed but especially revolutionary characters. This will involve street theatre as the buildup to the uprising, a few in-character speeches made (scripted, and you can have the script with you!) show flyers handed out to passers by. Will be alerting the Brixham News newspaper

Torquay Family Market – Sat August 31st, 1- 3pm “revolutionary rally” in Torquay Town Centre.  As many cast as can make it needed but especially revolutionary characters. This will involve street theatre as the buildup to the uprising, a few in-character speeches made (scripted, and you can have the script with you!) show flyers handed out to passers by. TFM have stated that they expect the local radio and newspapers to attend.

Admin and crew deadlines (aim for earlier if possible)

Blocking – blocking will begin May 29th, and basic blocking to be completed by June 26th.

Sound effects – by June 26th

Lighting effects – June 26th

Set (excluding barricade) – building complete by Aug 14th,

Set (barricade) - building complete by Sept 7th

Makeup – Makeup needs to come in to rehearse from Aug 21th

Publicity – rolling with deadlines relevant to publications, send to monthly publications and online events listings by June 30th, Brixham News and Herald Express by Aug 25th.

Scripts down – All actors must be off scripts by August 4th

Refreshments for front of house – Sept 18th

FOH training – Sept 18th  rehearsal (to be aware of show content, questions, etc)